## Sheet1
MTRN4230 Task Progress Table | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Progress Status |  |  | Prateek | Weber | Omar | Richard | Leo | Justin
1.0 RobotStudio (/4) | [5 empty] | incomplete | In progress | Complete
1.1 Define and display in Robotstudio with correct orientation:
1.1.1 0.25 ● World frame
1.1.2 0.25 ● Base frame
1.1.3 0.25 ● End effector frame
1.1.4 0.25 ● Table camera frame
1.1.5 0.25 ● Conveyor camera frame
1.1.6 0.25 ● Table home frame
1.1.7 0.25 ● Conveyor home frame
1.2 1.5 Display a recognisable CAD model of the Robot Cell and surrounding area. Include robot, walls, safety
switches, light curtain, conveyor, tables, computer, flex pendant, conveyor panel.
1.3 0.25 CAD model is coloured.
1.4 0.5 Move robot in simulation through the Matlab GUI when not connected to the real Robot System.
2.0 GUI:Startup and shutdown (/2.5)
2.1 0.5 At the start of the program. Display all the safety information contained in the SWP and prompt the user
for confirmation. Guide the user through the steps to operate the robot.
2.2 Provide a method to shutdown the robot:
2.2.1 0.5 ● Programmatically move the robot to home position
2.2.2 1 ● Avoid collision with the table.
2.2.3 0.5 ● Programmatically set all Digital Outputs (DOs) to 0
3.0 GUI:Robot status (/3)
3.1 0.5 Give a live update on the status of the robot.
3.2 0.5 Display the current robot joint angles.
3.3 0.5 Display the current end effector position.
3.4 0.5 Display the current end effector orientation.
3.5 0.5 Display a list of messages sent to the robot system in a human readable format.
3.6 0.5 Display a list of messages received from the robot system in a human readable format.
4.0 Safety system (/4)
Provide diagnostics on the GUI for all the conditions that prevent the robot from operating. The
diagnostics need to be displayed until the problem have been resolved. Prevent move commands from
being sent to the robot until the problem has been resolved.
4.1 0.5 ● Emergency stop
4.2 0.5 ● Light curtain
4.3 0.5 ● Motors are off
4.4 0.5 ● Hold to enable not pressed
4,5 0.5 ● Motion task not running/ Execution Error
4.6 0.5 ● Motion supervision triggered (Alternatively prevent the robot from being able to collide with the
table).
4.7 0.5 ● Conveyor is not enabled when trying to use the conveyor.
4.8 0.5 Set ConRun to 0 if ConStat is set to 0 and gracefully handle restarting of the conveyor.
5.0 DIO (/2.5)
Display the status of Digital Input/Output (DIO) and enable control of DIO from GUI through RAPID
5.1 0.5 ● Control vacuum pump
5.2 0.5 ● Control vacuum solenoid
5.3 0.5 ● Conveyor run
5.4 0.5 ● Conveyor direction
5.5 0.5 ● Conveyor enabled
6.0 GUI:Video feeds (/6)
6.1 0.5 Display a live video feed from the conveyor camera (min refresh rate: 1Hz).
6.1.1 1 ● Outline the edge of any boxes.
6.1.2 1 ● Visually indicate the orientation of any boxes.
6.2 0.5 Display a live video feed from the table camera (min refresh rate: 1Hz).
6.2.1 1 ● Outline the edge of all visible blocks on the table video feed.
6.2.2 0.5 ● Visually indicate the orientation of all visible blocks on the table video feed.
6.2.3 1 ● Indicate which letter is visible on the block.
6.2.4 0.5 ● Indicate if any block is unreachable
7.0 GUI:Pose (/6.5)
Able to move the robot to a pose using matlab. Need to be accurate to within 5 mm for full marks.
7.1 1 ● Move the end effector to a specified position relative to table home.
7.2 1 ● Move the end effector to a specified position relative to conveyor home.
7.3 1 ● Move to a specified pose (set of joint angles).
7.4 1 ● Reorient the end effector without changing the position of the tip.
7.5 1 ● Click on a position on the table video feed and move the end effector to that position (pointing
down).
7.6 1 ● Click on a position on the conveyor video feed and move the end effector to that position
(pointing down).
7.7 0.5 ● Able to move at different speeds.
8.0 GUI:Jogging (/4.5)
Able to move the robot continuously using matlab with continuous human input. Eg: using mouse,
keyboard or xbox controller. Motion need to be smooth for full marks.
8.1 1 ● Move the end effector in linear mode with respect to the base frame.
8.2 1 ● Move the end effector in linear mode with respect to the end effector frame.
8.3 1 ● Reorient the end effector without changing the position of the tip.
8.4 1 ● Jog any of the joints.
8.5 0.5 ● Able to move at different speeds.
9.0 RAPID:Motion (/6)
Able to move the robot to a pose using matlab, given a single command.
9.1 1 ● Move the end effector to a specified position relative to table home.
9.2 1 ● Move the end effector to a specified position relative to conveyor home.
9.3 1 ● Move to a specified pose (set of joint angles).
9.4 1 ● Reorient the end effector.
9.5 1.5 ● Move in linear motion mode.
9.6 0.5 ● Able to move at different speeds.
10.0 GUI:Pause and resume (/1.5)
10.1 0.5 ● Pause the current motion task, stop the robot from moving.
10.2 0.5 ● Resume the current motion task, continue the previous move command.
10.3 0.5 ● Cancel the current motion task, stop the robot, prepare for new move command.
11.0 RAPID:Pause and resume (/3)
11.1 1 ● Pause the current motion task, stop the robot from moving.
11.2 1 ● Resume the current motion task, continue the previous move command.
11.3 1 ● Cancel the current motion task, stop the robot, prepare for new move command.
12.0 Error handling (/4)
12.1 1 Handle all communication errors in RAPID without needing to restart tasks.
12.2 1 Handle all communication errors in Matlab without needing to restart the GUI (including incorrect IP
address, socket timeout, unable to connect to the robot).
12.3 1 Advise the user if a move command is unreachable.
12.4 1 Advise the user if network connection is lost.
13.0 Documentation (/5)
13.1 1 Evidence of proper code version management. Showing each student’s contribution. git commit log
All code must be well structured and documented. Use appropriate variable and function names.
13.2 1 ● Matlab – Include usage example and help command.
13.3 1 ● RAPID
13.4 1 Document the communication protocol used to communicate between Matlab and RAPID. The structure
of the message, what each field represents, valid value.
13.5 1 List of tasks assigned to each member and indicate percentage completion.
14.0 Testing (/7.5)
Develop and document a test plan (to show to your demonstrator) and write test functions for
14.1 1 ● GUI:Robot status (Hint: Jog robot to a position, check the display).
14.2 1 ● GUI:Video feeds (Hint: Check block are displayed correctly).
14.3 1.5 ● Communication protocol (Hint: print human readable information on flex pendent and matlab).
14.4 3 ● GUI:Pose and RAPID:Motion (Hint: Do a move command and check the robot position).
14.5 1 ● DIO (Hint: Test DIO).
The test plan should include a number of test cases with procedure, required human input, and
expected outputs. Testing should be easy to use and automated when possible. All requirements in
each section need to be tested. More than one test case per requirement may be requested.